## Sheet1
Product Backlog
ID | Name | Importance | Estimate | How to demo | Notes
1 | Login for student | Qualified guess 60 | 1 | Login as a student and show | Only basic safety is to be implemented
|  |  |  | that it is successful. | No SSL layer reqd.
Make entity classes, with attributes,
store hashed value. Compare with login.
2 | Login for teacher | 70 | 1 | Login as a teacher and show | Only basic safety is to be implemented
|  |  |  | that it is successful. | No SSL layer reqd.
Make entity classes, with attributes,
store hashed value. Compare with login.
3 | Teacher sets up period | 160 | 1 | Show setting up of period | Teacher can set maximum marks and
required marks. Use http POST in the REST
api. Frontend w/Angular JS
4 | Teacher sets up descripti- | 150 | 1 | Show setting up of descripti- | Description for score tasks is in two parts
| on for score task |  |  | on and addition to database | Part 1: for attendance
Part 2: for Cas
Use http POST in the REST api.
Frontend w/Angular JS.
5 | Teacher adds/edits scores | 140 | 2 | Show adding.editing for arb- | Use http POST and PUT methods in REST-
|  |  |  | itrary student | API. Now MONGO will be used as the
database. Non relational database.
Implement frontend with AngularJS
6 | Teacher sees points for | 130 | 1 | Show getting points for | Use http GET in the REST api. Use mongo.
| attendance for a day |  |  | student/ whole class | Implement frontend with AngularJS
7 | Teacher sees points for | 120 | 1 | Show getting points for | Use http GET in the REST api. Use mongo
| a task(CA) |  |  | specified CA for | Implement frontend with AngularJS
student/whole class
8 | Teacher sees all points | 110 | 1 | Show getting points for a | Use http GET in the REST api. Use mongo.
| for a period |  |  | specified period for a single | Implement frontend with AngularJS
student/ whole class
9 | Teacher sees all points | 100 | 1 | Show getting points for a | Use http GET in the REST api. Use mongo
| for a semester |  |  | specified semester for a | Implement frontend with AngularJS
single student/whole class
10 | Teacher sets up a new | 200 | 1 | Show successful addition of | Use a form with a submit button in the
| teacher manually |  |  | a teacher to the system | frontend.
This forms data is posted to the database
using http POST in the REST api
11 | Teacher sets up multiple | 180 | 1 | Show successful addition of | Use a form with a submit button in the
| new teachers |  |  | multiple teachers to the | frontend. In the form we will have the
|  |  |  | system. | option teacher/student and \in this case
we select teacher
Separate the values between commas.
Add each gotten value separately to the
teachers database using POST in the REST
api
12 | Teacher sets up new | 190 | 1 | Show successful addition of | Use a form with a submit button in the
| student manually |  |  | a student to the system | frontend.In the same form select student.
This forms data is posted to the database
using http POST in the REST api
13 | Teacher sets up multiple | 170 | 1 | Show successful addition of | We click on a button, which uploads a
| new students |  |  | multiple students to the | file to the database.
|  |  |  | system | Separate the values between commas
Add each gotten value separately to the
teachers database using POST in the REST
api
14 | Student sees points brea- | 90 | 1 | Show student accessing the | The access is made using the http GET
| kup for task/semester |  |  | info | method. The frontend is implemented
using angularJS.
15 | Student sees points for | 80 | 1 | Show students accessing the | The access is made using the http GET
| himself/herself |  |  | info | method. The frontend is implemented
using angularJS.
The points are seen for day/period/
semester.
16 | Student changes password | 50 | 1 | Show student changing pass | The change is made using http PUT
|  |  |  | word | method in the REST api. Frontend is
a simple form which uses angularJS.