## Sheet1
| RELEASE PLAN | (Velocity=17)
Importance | Name | Estimate
200 | Teacher sets up a new | 1
teacher manually
190 | Teacher sets up new | 1
student manually
180 | Teacher sets up multiple | 1
new teachers
170 | Teacher sets up multiple | 1
new students
160 | Teacher sets up period | 1
SPRINT 01
150 | Teacher sets up descripti- | 1
on for score task
140 | Teacher adds/edits scores | 2
130 | Teacher sees points for | 1
attendance for a day
120 | Teacher sees points for | 1
a task(CA)
110 | Teacher sees all points | 1
for a period
SPRINT 02
100 | Teacher sees all points | 1
for a semester
90 | Student sees points brea- | 1
kup for task/semester
80 | Student sees points for | 1
himself/herself
70 | Login for teacher | 1
60 | Login for student | 1
50 | Student changes password | 1
SPRINT 03